## Dev Budget
MSA 1 EXPANSION
Magnolia Science Academy, San Diego |  |  |  | Ground Lease; Site Improvement
SDUSD DeAnza Elementary School Site, 6525 Estrella Ave., San Diego, CA 92120
2017-02-01
Uses |  | $ | Sources |  | $
Acquisition |  | 3840000
Soft Costs |  | 563530 | MERF Permanent Financing |  | 9808930
Hard Costs |  | 5405400
Total Project Costs |  | 9808930 | Total Sources |  | 9808930
Dev Budget-NEW CONSTRUCTION | [5 empty] | PROJECT INFO | SF | APN | Zoning
Existing SF (land) | 44669.6 | Building SF | 16845.6 |  |  | PARCEL 1 | 16845.6 | 2125036021 | [Q]C2-1L-CDO
Total Proposed SF | 25200 | Stories | 2 |  |  | PARCEL 2 | 21994.6 | 2125036105 | [Q]P-1L-CDO
Students | 500 |  |  |  |  | PARCEL 3 | 5829.4 | 2125036106 | [Q]P-1L-CDO
SF Per Student | 50.4 |  |  |  |  | Total SF | 44669.6
General Plan Land Use: Community Commercial
| Amount | Per SF | Per Student |  |  | Max Stories: 6
Acquisition | 3800000 | 85.069 | 7600 |  |  | Total Buildable Area: FAR 1.5
Closing Costs | 40000 | 0.89546 | 80 |  |  | Total Max Buildable Square Footage:
Acq Total | 3840000 | 85.9645 | 7680 |  |  | 25239
Hard Cost | 4914000 | 195 | 9828
Contingency @ 10% | 491400 | 19.5 | 982.8
Hard Cost Total | 5405400 | 214.5 | 10810.8
Soft Costs | 512300 | 20.3294 | 1024.6
Contingency | 51230 | 2.0329 | 102.46
Soft Costs Total | 563530 | 22.3623 | 1127.06 |  | 4914000
200000
Total Project Costs | 9808930 | 389.2433 | 19617.86 |  | 4714000
471400
PROJECT FINANCING
Total Project Costs | 9808930
Sale of Lots | 0
Amount to be Financed | 9808930
Assumptions
1. Return of $1MM in equity for ACQ
2. FAR met
3. Two Story at Grade, Rooftop Area
4. Begin Demo 7/1/17
5. Occupancy August 2018

## Sheet2
| January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September
Soft Costs |  | 65383.33 | 85383.33 | 85383.33 | 65383.33 | 55383.33 | 55383.33 | 15000 | 15000 | 15000 | 15000 | 10000 | 10000 | 10000 | 10000 | [6 empty] | 512299.98
Hard Costs | July: 200000; August: 471400; September: 471400; October: 471400; November: 471400; December: 471400; January: 471400; February: 471400; March: 471400; April: 471400; May: 471400 | 4914000
5426299.98