## Slide 1: Magnolia Science Academy, Santa Ana, CA
Gymnasium Project

## Slide 2: Overview
  Project Summary
  Project Schedule Update
  Project Documentation
  Financial Report
  Progress Photos

## Slide 3: Project Summary
Project is approximately 22% complete
Project Submittals are 97% complete
Procurement of structural steel in process
Project construction meetings on going, Tuesdays at 9:00 am
Contractor’s payment application #04 has been reviewed

## Slide 4
Project Schedule Update
Schedule Milestones
  Construction Completion date: August 15,2018
  Presently the project is on schedule
  Contractor’s has submitted March 2018 update construction schedule
Upcoming Construction Activities
  Erection of Exterior and Interior Masonry Wall on going
Construction Impacts to the General Campus and Local Community
  No impacts to school activities are anticipated during the next 30 days

## Slide 5
Project Documentation
Submittals
  As of February 28, 2018, 83 submittal packages have been issued by the contractor.
  The Architect has approved 52 submittal packages.
  The Architect has returned 10 submittal package to be revised and resubmitted.
  21 submittals either have been closed or are currently with the Architect for review
RFI’s
  As of February 28, 2018, 66 RFI’s have been issued by the contractor
  7 remain open with none of those being critical

## Slide 6
Project Documentation
Architect’s Supplemental Instruction
  ASI #1 Add Alternate (RC Construction currently putting together a cost proposal)
    Rubberized Gym Flooring
  ASI #2 Deductive Alternates (RC Construction Currently Putting together a cost proposal)
    Removal of glazing at east gym wall and replacing CMU block
    Eliminate graffiti coating on exterior gym walls
    Modify concrete floor finishes
    Remove lockers
    Remove carpet tile

## Slide 7
Financial Report
Change Order
  Change Order Log
    Non-Compensatory Time Extension: 94 Days
  Potential Change Order Log
  Contingency Draw Downs- Final Agreed to Cost
Contingency Starting Balance | $ 112,544.89
PCO #02 Provide Power to Fire Alarm | $ 3,440.25
PCO #03 Provide Power to Water Heater | $ 1,096.33
Contingency Balance as of Febraury 28,2018 | $ 108,008.31
PCO #02 | Contractor to provide and install power for fire alams |  |  |  | RFI #34 | Negotiations | 01/30/18 | $ 3,826.00 | $ 3,055.47 | $ 770.53 | $ 3,440.25 | 0 | Cost to be drawn from project contingency |  | 
PCO #03 | Contractor to provide and install power for water heater |  |  |  | RFI #29 | Negotiations | 01/30/18 | $ 1,311.00 | $ 852.82 | $ 458.18 | $ 1,096.33 | 0 | Cost to be drawn from project contingency |  | 
4 | Potential Cost Associated w/Fire Sprinkler Riser |  |  |  | N/A | Pending |  | $ 7,000.00 |  |  |  |  | ROM, COR not submitted by RC |  | 
5 | Power to raise & lower basketball back boards |  |  |  | NA | Pending |  | $ 14,000.00 |  |  |  |  | Cost is only ROM from GC |  | 
 | Contractor total | Gafcon Total | Agreed Amount
PCO #02 Provide Power to Fire Alarm System-Submitted | $ 3,826.25 | $ 3,055.47 | $ 3,440.25
PCO #03 Provide Power to Water Heater- Submitted | $ 1,311.00 | $ 852.82 | $ 1,096.33
Modifications to Fire Sprinkler Riser- Pending | $ 7,000.00 |  | 
Power to raise & Lower Basketball Back Boards-Pending | $ 14,000.00 |  | 

## Slide 8: Financial Report

## Slide 9: Financial Report
Project Contract and Billings to Date
RC Construction Services Base Contract | $ 3,864,041.36
Invoice as of January 28,2018 (Pay Apps No. 01-No. 03) | $ 541,431.07
Remaining Balance as of January 31,2018 | $ 3,322,610.29
Berliner Architects Total Contracts Amounts | $ 219,090.00
Invoice as of January 28,2018 | $ 34,334.29
Remaining Balance as of January 31,2018 | $ 184,755.71
Gafcon Total Contract Amounts | $ 184,619.00
Invoice as of Janaury 31,2018 | $ 126,364.10
Remaining Balance as of January 31,2018 | $ 58,254.90
Inland Inspection Services Contract Amount | $ 114,075.00
Invoiced as of January 28,2018 | $ 32,448.00
Remaining Balance as of January 31,2018 | $ 81,627.00
River City Testing Contract Amount | $ 52,882.00
Invoiced as of January 28,2018 | $ 3,162.25
Remaining Balance as of January 31,2018 | $ 49,719.75

## Slide 10: Progress Photos

## Slide 11: Progress Photos

## Slide 12: Progress Photos

## Slide 13: Board Q&A