## 2017-2018 Dashboard- orginal (hidden)
# | GOAL/KEY MILESTONES | HOT Owner | 2017-10-27 | 2017-01-26 | 2017-04-27 | 2017-07-27
1 | v1 of Impact Public School’s Operating Manual that articulates the organization’s policies and procedures will be publicly available by July 1, 2018 | Noah
1.1 | Outline drafted, including Parent Handbook and Employee Handbook |  | x
1.2 | 50% of manual drafted |  |  | x
1.3 | First draft ready for external review |  |  |  | x
1.4 | v1 posted on IPS website |  |  |  |  | x
2 | Impact ¦ PSE’s building is ready to receive staff and students by August 1, 2018. This will be measured by: - <5 items remain on renovation punchlist - interior and exterior design in consistent w/IPS brand - All furniture, classroom supplies, materials are in place - All computers and related IT hardware and software is available and functionable | Noah
2.1 | Financing closed/building owned by IPS |  | x
2.2 | Construction contracts in place that require work to be completed by 8/1 |  |  | x
2.3 | All furniture, fixtures & equipment (FFE) ordered |  |  | x
2.4 | Renovation work begun |  |  |  | x
2.5 | Renovation substantially completed |  |  |  |  | x
2.6 | All FFE received and installed |  |  |  |  | x
2.7 | Certificate of Occupancy received |  |  |  |  | x
3 | By August 2018, IPS and Impact ¦ PSE will have the necessary start up and operating funds and a balanced 5 year financial forecast | Jen/Noah
3.1 | Board approves FY17-18 operating budget |  | x
3.3 | Fundraising plan and materials ready |  |  | x
3.2 | By TBD 2018, Impact ¦ PSE will have a revised and balanced operating 2018-2019 budget and 5 year financial plan based on actual OSPI per pupil amounts. |  |  |  | x
3.4 | 90% of 2017-2019 start up funding raised |  |  |  |  | x
3.5 | Board approves FY18-19 operating budget |  |  |  |  | x
4 | Impact ¦ PSE has all the systems and operations in place by August 2018 that ensure students and staff are able to focus their time and attention on learning. As measured by: - Contracts established for food service, custodial services, transportation, special education, SIS - Student schedules are ready - On track w/Commission's pre-opening conditions | Noah
4.1 | Dir of School Ops hired |  |  | x
4.2 | All necessary support contractual needs identified and RFPs issued |  |  | x
4.3 | On track w/Charter Commission pre-opening conditions |  |  | x | x | x
4.4 | Contracts in place |  |  |  | x
4.5 | Succesful Pre-Opening Site Visit from Charter Commission |  |  |  |  | x
4.6 | School opening manual drafted |  |  |  |  | x
5 | All curriculum, assessment, instructional & culture practices and corresponding professional development are curated or built, tested, refined and stored by July 2018. | Jen
5.1 | Ed model work plan fully developed |  | x
5.2 | Studio vendors selected & PBL partners named |  | x
5.3 | Pilot launched with clear Build/Measure/Learn process in place |  |  | x
5.4 | All materials stored in PLP or google drive & all contracts in place |  |  |  | x
5.5 | Professional development and coaching plan fully developed |  |  |  |  | x
6 | The IPS Board is comprised of 7 diverse (race, region, gender & expertise) and actively engaged board members. 50%+ leaders of color by July 27, 2018. | Jen
6.1 | 6th board member appointed |  | x
6.2 | 100% participation in board sign up for community events in planning year |  | x
6.2 | 7th board member appointed |  |  | x
6.3 | Officers are elected |  |  | x
6.4 | Committees launched, meeting schedule set & cadence drafted |  |  |  | x
6.5 | 100% participation at ribbon cutting & 100% participation in board sign up for community events during year 1 |  |  |  |  | x
7 | 100% of founding faculty return for 2018-2019 and are living the IPS mission and values | Jen
7.1 | IPS goals, milestones and work plans are set. IPS goals shared with board for feedback. |  | x
7.2 | Individual team member goals are set with personal PD plans & coaching in place |  | x
7.3 | Decision making protocol selected and shared w/board |  | x
7.4 | Faculty survey drafted (aligned to Core Values) |  | x
7.5 | 1st faculty survey proctored & results/analysis shared with team/board (Dec 2017) |  |  | x
7.6 | Mid year coaching reflections complete |  |  | x
7.7 | Faculty survey refined (aligned to Core Values) |  |  |  | x
7.8 | 2nd faculty survey proctored & results/analysis shared with team/board. Strategy for year 1 shared with board for feedback. (June 2018) |  |  |  |  | x
7.9 | End of year coaching reflections complete w/ IPS & individual goals for 2018-2019 set. IPS goals shared with board for feedback. |  |  |  |  | x
8 | Teaching team (6 teachers, 3 teaching fellows) is fully hired by end of April 2018. All teachers meet IPS "high bar." | Jen
8.1 | Recruitment, selection and hiring process in place |  | x
8.2 | First IPS Simulation Day complete with 50% faculty hired |  |  | x
8.3 | Second IPS Simulation Day complete with 100% faculty hired |  |  |  | x
8.4 | Recruitment, selection and hiring process is codified & ready for replication |  |  |  |  | x
9 | Narrowed greenlighting list to 3 locations for school 2 by August 2018 | Noah
9.1 | Present greenlighting tool and get board approval |  | x
9.2 | Identify 5-7 locations to run through greenlighting tool |  |  | x
9.3 | Generate scores for all locations using tool |  |  |  | x
9.4 | Based upon both scores and intuition of IPS team, narrow list to 3 locations |  |  |  |  | x
10 | Impact I PSE will be 100% fully enrolled with a 20% waitlist on day 1 with a heterogenous population that mirrors the district | Natalie
10.1 | Recruitment plan complete and faculty is fully trained |  | x
10.2 | 100 students accepted by Nov 30 lottery |  |  | x
10.3 | 280 applications; 160 students fully enrolled with all enrollment paperwork complete |  |  |  | x
10.4 | 180 students fully enrolled with all enrollment paperwork complete |  |  |  |  | x
11 | By August 2018, Impact I PSE will be an active and respected partner in the Tukwila community as measured by | Natalie
11.1 | All Home Office faculty & school leaders have selected & engaged with 1 local organization to be an active participate |  | x
11.2 | Pilot program in place with Tukwila SD |  |  | x
11.3 | Community stakeholder presentation (State of IPS) executed |  |  |  | x
11.4 | Community park open w/ large community event & positive press |  |  |  |  | x
12 | IPS is becoming a model for public education across WA as measured by: 500 Twitter followers, 500 FB friends, 4,000 enews contacts and 2 positive articles | Jen/Natalie
12.1 | Communications plan is complete and shared with board, including story board for enews, blog and social media + quarterly earned media events |  | x
12.2 | Website is fully built out |  | x
12.3 | Fall enews communication disseminated + first earned media event |  | x
12.4 | Winter enews communication disseminated + second earned media event |  |  | x
12.5 | Spring enews communication disseminated + third earned media event |  |  |  | x
12.6 | Summer enews communication disseminated + fourth earned media event + 100+ people at ribbon cutting event |  |  |  |  | x

## 2021 Preopening Dashboard
# | GOAL/KEY MILESTONES | HOT Owner | March | April | May | June | July | August
1 | PCM will be 100% fully enrolled with a 20% waitlist on day 1 with a student demographics meeting the targets outlined in the charter application and WA Charters Grant Agreement | Jen
Complete | Recruitment plan complete and faculty is fully trained
Complete | 50% of students fully enrolled with enrollment paperwork complete (Required Essential Milestone) |  |  | x
Complete | 80% of students fully enrolled with enrollment paperwork complete (Required Essential Milestone) |  |  |  | x
In Progress | 100% of students fully enrolled with all enrollment paperwork complete (Required Essential Milestone) |  |  |  |  | x | x
In Progress | 120% applications submitted; waitlist is 20% enrollment capacity
In Progress | Student demographics meet the target demographics outlined in charter application and WA Charters Grant | [6 empty] | x
2 | All curriculum, assessment, instructional & culture practices and corresponding professional development are curated or built, tested, refined and stored by July 2021. | Jen
Complete | Curriculum providers selected. If creating or modifying any curriculum, school has crriculum design selected and work started. |  | x
Complete | All materials stored in google drive (or other storage system) & all contracts in place |  | BOX (minimal Google Drive)
In Progress | All critical materials, curricula, and technology has been ordered. |  |  | x
In Progress | Detailed unit/project plans, lesson plans, and assessments for first half of the school year in all grade levels are complete and submitted to WA Charters and the Commission. | [5 empty] | x
LMS built out with curriculum
In Progress | Multi-tiered system of supports (MTSS) plan completed, including for special populations and ready for implementation | [5 empty] | x
In Progress | Professional development and coaching plan fully developed | [5 empty] | x
3 | All staff is fully hired by July 2021. | Jen
Complete | Recruitment, selection, and hiring plan complete
Complete | 50% of staff hired |  |  | x
In Progress | 90% of staff hired |  |  |  |  | x
In Progress | 100% of staff hired | [5 empty] | x
In Progress | Global Majority staff members make up at least 18% of the staff population (at least 10% higher than district in which school is located) | [5 empty] | x
Complete | Recruitment, selection, and hiring process is codified & ready for replication | [6 empty] | x
4 | PCM will be an active and respected partner in the Pullman community. | Jen
Each leadership team member has selected & engaged with 1 local organization to be an active participate
Community stakeholder presentation executed
Community park open w/ large community event & positive press
5 | PCM's building is ready to receive staff and students by August 1, 2021. | Noah
Complete | School has a viable long-term facility pathway (3 years and beyone) identified |  |  | x
In Progress | Financing closed
Complete | Construction contracts in place with timeline assurances that zoning, permitting, and construction will be completed in time for opening |  |  | x
Complete | All furniture, fixtures & equipment (FFE) ordered |  |  | x
Renovation work begun
| Renovation substantially completed | [5 empty] | x
| All FFE received and installed | [5 empty] | x
| Certificate of Occupancy received | [6 empty] | x
6 | PCM has all the systems and operations in place by August 2021 that ensure students and staff are able to focus their time and attention on learning. | Noah
In Progress | All necessary support contractual needs identified and RFPs issued
Complete | On track w/Charter Commission pre-opening conditions
Complete | Contracts in place
| Succesful Pre-Opening Site Visit from Charter Commission |  |  |  |  | X
In Progress | School Operations Manual is drafted and ready for faculty use.
7 | PCM will have the necessary start up and operating funds and a balanced 5 year financial forecast | Jen/Noah
In Progress | Fundraising plan completed
Complete | PCM will have a revised and balanced operating 2021-22 budget and 5 year projected budget is viable and shows sustainability on public funds within five years. |  | x
In Progress | School has a federal and state grant application status tracker for SY 2021-22
Board approves FY21-22 operating budget and 5 year budget projection
8 | PCM's Board is comprised of diverse (race, region, gender & expertise) and actively engaged board members. | Jen
Complete | Board consists of at least 2 members with prior experience on successful nonprofit boards |  | x
Complete | Board consists of at least 1 member with finance expertise |  | x
Complete | Board consists of at least 1 member with K-12 expertise |  | x
In Progress | Board is representative of different subgroups the school will serve |  | x
Complete | Officers are elected
In Progress | Committees launched, meeting schedule set & cadence drafted
Not Yet Started | 100% participation at ribbon cutting & 100% participation in board sign up for community events during year 1
9 | v1 of PCM’s comprehensive Master Policy Manual, including the Parent Handbook, Employee Handbook and Operations Manual, that articulates the organization’s policies and procedures will be publicly available by July 1, 2021 | Noah
In Progress | Outline drafted, including Parent Handbook and Employee Handbook
Complete | 50% of each component drafted
Not Yet Started | Final drafts ready for board review and adoption |  |  |  |  | x
Not Yet Started | v1 posted on PCM's website
Not Yet Started
In Progress
Complete
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OSPI Report Card (District level report): 92% white, 5% 2 or more races, 2% Latinx, 1% not provided, 0.5% America Indian/Alaskan Native. 73% female (much higher at elementary...90-95%)