Logo, company name

Description automatically generated

**Shared Values ~ Vision ~ Mission**

**Project Timeline**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Anticipated Completion Date | Activity/Exercise | | | Stakeholder Group Involved | Facilitator | |
| 11/28  12/1  12/9  TBD  TBD  TBD  Early January | | Review Shared Values  Calibrate Shared Values among stakeholder groups | District Improvement Team  Board of Trustees  Leadership Team  Elementary School  Middle School  High School | | | Eddie  Amanda/Eddie  Alisa / Eddie  Mike/ Eddie |
| Early January  Late January | | Develop Concept Statements  Calibrate Concept Statements among stakeholder groups | District Improvement Team  Board of Trustees  Leadership Team  Elementary School  Middle School  High School  Families | | |  |
| Early February  Late February | | Review / Reimagine Vision  Calibrate Vision among stakeholder groups | District Improvement Team  Board of Trustees  Leadership Team  Elementary School  Middle School  High School  Families | | |  |
| Early March  Late March | | Review/ Reimagine Mission  Calibrate Mission among stakeholder groups | District Improvement Team  Board of Trustees  Leadership Team  Elementary School  Middle School  High School  Families | | |  |