## Slide 1: DIVERSITY EQUITY INCLUSION ADVISORY COMMITTEE
February 6, 2020
Board Meeting

## Slide 2: ROADMAP
Assessment
Oct
2019
Analysis
Nov - Feb
2019
Pre-
Implementation
Mar-Jul
2020
Implementation
Aug 2020 -
May 2021
Post-
Assessment
May-Jun 2021

## Slide 3: Phase 2: Analysis
Goal: Analyze Data With Divisions
Use staff voice to gather feedback and context behind division data related to trust, inclusion, and conflict.
Use feedback from staff to tailor upcoming work with each division.
Notes: Key difference is that RISA asks about students

## Slide 4: Phase 2: Analysis
Update
Jan- Feb | DEI Advisory - Identify specific data points to gather staff feedback on | Complete
Feb | DEI Advisory - Plan Data Analysis Meeting Dates with each division | In Progress
March (extended timeline) | CircleUp Education - Lead Data Analysis Meetings with each division | Not Started
Notes: Key difference is that RISA asks about students

## Slide 5: Phase 5: Pre-implementation
Goal: Prepare MWA for the DEI Journey
Increase Trust Within Divisions And Across the School
Feb - March | DEI Advisory - Plan 1-2 PD Dates for Each Division | Not Started
March | CircleUp Education - Customize PD’s based on Data Analysis | Not Started
March- June | CircleUp Education - Facilitate 1-2 PD with Each Division | Not Started
July - August | DEI Advisory - Reassess and plan for 2020-2021 | Not Started
Notes: Key difference is that RISA asks about students

## Slide 6: Diversity Equity and Inclusion (DEI) COMMITTEE
Alton B. Nelson Jr. CEO
Jessica (Wind) Laughlin Board Member
Eric Mingo Director Diversity & Inclusion
Elizabeth Martinez Chief of Staff
Danilo Garcia Middle School Social Worker
Michelle Chan Academic Advisor
Eric Abrams Community Member
Tiffany Hoang Consultant